Fair Employment Wage Board Meeting

Thursday, April 24, 2025

1 PM

- Call meeting to order

- Review and approve minutes of last meeting

- Introductions of board members and city/county staff

- Ice breaker – Getting to know you!

- Set meeting dates for 2025

- Review draft outline for activities of 2025 to get action!

  - Discussion & Volunteering

- Optional: Visioning Exercise – Headline Exercise

- Recap & Adjourn

Note: Minutes listed as guide and would not be included in agenda to board members.

Deliverables & Implementation Plans:

The main activities of this body may best be moved forward with a few working groups, such as:

- Vision statement & bylaws.

- Enforcement procedures with the city of Cleveland.

- Partners for education of employers and workers.

- Other?

The draft overall plan for our meetings may be as follows:

| Activity | Meeting | Meeting Goals | Work between |
| --- | --- | --- | --- |
| Visioning Exercise | April | Set meeting dates for 2025 | Working groups meet and confirm an agenda and Ryan secure examples of vision statements and bylaws |
| Start working on vision statement, bylaws and enforcement procedures | May | Confirm date of enforcement of ordinances | Work on vision statements and bylaws |
| Review best practices from around the state and nation | June | Adopt vision statement and bylaws | Work on enforcement procedures for ordinances and outreach efforts |
| Review enforcement procedures | July | Adopt enforcement procedures, if possible | Plan Labor Day weekend event announcing protection |
| Discuss partners and outreach starting with Labor Day weekend event | August | Plan kick-off in time for Labor Day weekend. | Plan briefings for more partners |
| Follow up with administration on enforcement | September | Celebrate kick-off! | Discussion with partners |
| Listening to enforcement staff | October | Discussion on reaction from partners – what did we learn? | Start planning for 2026 |
| Start setting agenda for 2026 | November | Draft 2026 agenda | Listen to workers |
| Set agenda for 2026 and listen to workers assisted | December |  |  |

Optional Visioning Session

(Depending on time at our April 24th Board meeting)

We will move to a couple of small groups of 3-4 board members.  You will select different teammates than you had in the earlier ice breaking exercise.

Each team will brainstorm a headline that we would like to see at the end of the year to illustrate the work we discussed during the board meeting.

We suggest creative and bold headlines.

After a brief brainstorming session in a couple of teams, we will share them with one another then have a short discussion on our values that are reflected in the headlines.

###